| [Your Business Name] [Street address] [City, State ZIP] [email@yourbusiness.com] [(555) 555-0123] | INVOICE |
| --- | --- |

| BILL TO [Client Name] [Street address] [City, State ZIP] [client@email.com] | Invoice number: PAY-03 Invoice date: [Date] Due date: [Date] (Net 30) Project: [Project name and address] Contract no.: [Contract number] Period to: [Billing period end date] |
| --- | --- |

| Item | Amount |
| --- | --- |
| Framing: 100% complete Scheduled value $42,000; previously billed $25,200 | $16,800.00 |
| Rough electrical: 60% complete Scheduled value $18,500 | $11,100.00 |
| Rough plumbing: 50% complete Scheduled value $16,000 | $8,000.00 |
| Change order #2: added window, approved [date] | $4,200.00 |
| Less retainage, 10% | -$4,010.00 |

| Subtotal | $36,090.00 |
| --- | --- |
| Total | $36,090.00 |

NOTES

Pay application 3, work through [date]. Contract sum $186,000.00; change orders to date $4,200.00. 10% retainage withheld until substantial completion.

HOW TO PAY

Payment: [Bank name] · Account [number] · Routing [number], or [other ways to pay]