## Invoice
[Your Business Name] |  |  | INVOICE
[Street address]
[City, State ZIP]
[email@yourbusiness.com]
[(555) 555-0123]
BILL TO |  | Invoice number | PAY-03
[Client Name] |  | Invoice date | [Date]
[Street address] |  | Due date | [Date] (Net 30)
[City, State ZIP] |  | Project | [Project name and address]
[client@email.com] |  | Contract no. | [Contract number]
|  | Period to | [Billing period end date]
Item | Qty | Rate | Amount
Framing: 100% complete — Scheduled value $42,000; previously billed $25,200 | 1 | 16800 | 16800
Rough electrical: 60% complete — Scheduled value $18,500 | 1 | 11100 | 11100
Rough plumbing: 50% complete — Scheduled value $16,000 | 1 | 8000 | 8000
Change order #2: added window, approved [date] | 1 | 4200 | 4200
Less retainage, 10% | 1 | -4010 | -4010
|  | Subtotal | 36090
| Tax rate | 0% | 0
|  | Total | 36090
|  | Amount paid | 0
|  | Balance due | 36090
NOTES
Pay application 3, work through [date]. Contract sum $186,000.00; change orders to date $4,200.00. 10% retainage withheld until substantial completion.
HOW TO PAY
Payment: [Bank name] · Account [number] · Routing [number], or [other ways to pay]